## Slide 1
OpenDaylight Packetcable Plugin
Working Group Call
October 20, 2016
Notes: Segue slide.

## Slide 2: Agenda
ODL Release Schedule
Newly Closed Issues
Open Issues
Q&A
Meeting Attendees:
Ryan Vail, Phil Rosenberg-Watt, Mufaddal Makati, Jeff Pedigo, John Tompson, Kasim Inan, Mohammad Kabir Chowdhury, Sameer, Vineesha Bandi

## Slide 3: List & Wiki
Mailing list :
  https://lists.opendaylight.org/mailman/listinfo/packetcable-dev
Wiki :
  https://wiki.opendaylight.org/view/PacketCablePCMM:Main

## Slide 4: Carbon: Draft Release Plan Milestones
M1 – Intent to participate – 11/3/16
M2 – Project Release Plan complete – 12/8/16
M3 – Feature / Function Freeze: 2/2/17
M4 – API Freeze: 3/2/17
M5 – Code Freeze: 3/30/17
RC0 / RC1 / RC2: 4/12/17, 4/20/17, 4/27/17
Packetcable Project Release Review – Between 4/27 & 4/3/17
RC3 – Release Review and final build: 5/4/17
Formal Carbon Release: 5/11/17

## Slide 5: Packetcable Carbon Goals / TODOs
Goals:
  fix identified bugs
  add enhancements; Comcast/AB list organized/grouped into sensible packages
Maintenance work
  Currently reported issues: none besides Comcast “package” (see slide 9)
Documentation work
  As needed to support new features / functions
Functional Changes
  Enhancements from Comcast / AB
Structural issues
  Change to support DataTreeChangeListener.- Bugzilla 6302

## Slide 6: Recently Completed Work Items
Notes: Segue slide.

## Slide 7: Packetcable Work Items – Update Docs
Source: Arris
  Integrate Arris information into current Packetcable User Guide.
Tracked on ODL Bugzilla - Bug 6279
Description: Documentation update
Type: Enhancement
Target Release: Carbon w/ “cherry pick” to Boron
Status: Done. Merged into Carbon and Boron.

## Slide 8: Packetcable Work Items – GateSpec Direction
Source: Comcast/AB
  List of bugs TBD
Tracked on ODL Bugzilla – Bug 6762
Description:
  Updates to support new TrafficProfiles that require a user-specified Direction in the GateSpec
Type: Task
Target Release: Carbon
Status: Done. Merged into master. Completed by Jeff Pedigo – Applied Broadband

## Slide 9: Open Work Items
Notes: Segue slide.

## Slide 10: Packetcable Work Items – Update to DTCL
Source: Comcast
  Submitted 6/30/16.
Tracked on ODL Bugzilla - Bug 6302
Description:
  OpenDaylight will deprecate and remove the DataChangeListener class, replacing it with DataTreeChangeListener. DCL class will remain deprecated through the Carbon release and removed subsequently.
  The Packetcable project needs to be revised to use DTCL in the Carbon Timeframe
Type: Task
Target Release: Carbon
Status: Issue assigned to Mufaddal Makati – CableLabs team

## Slide 11: Packetcable Work Items – Priority Classifier
Source: Comcast/AB
  List of bugs TBD
Tracked on ODL Bugzilla - Bug 6763
Description:
  Add support for the PCMM Priority parameter in all classifiers
Type: Bug
Target Release: Carbon
Status: Issue assigned to Jeff Pedigo – Applied Broadband

## Slide 12: Supporting Information
Comcast-submitted issues for resolution in next ODL release (Carbon)
9/15: Jeff Pedigo (Applied Broadband) will be working to submit a first set of changes to prove out the submission and review process.
Issues listed on row 7 (Fixed handling of Priority classifier parameter) and row 8 (Added direction to the GateSpec) from the list on the attached spreadsheet are the first to be processed.

## Slide 13: Open discussion
Q & A –
  Discussion for Packetcable Carbon release.
  Sameer Patel confirmed (on 10/3) that Comcast changes can comply with ODL Inbound Code Review requirements. https://www.opendaylight.org/InboundCodeReview#dco-policy

## Slide 14: WG Logistics
Meet every other week –
  Meeting dates to end of year are: Oct. 20, Nov. 3, Nov. 17, Dec. 1, & Dec 15
Continue to meet at 11:00 Mountain Time